## Slide 1
BEL Connections Journey

## Slide 2
Connection Steps with brief house descriptor
Understand your options, the process and the timelines with your service providers and our web self-service tools.
Assessing your electricity supply options.
Confirming your solution and costs.
Building your electricity supply.
Connecting your electricity supply.
Level
1
2
Enquire & Discuss
Apply & Explore
Design & Approve
Deliver & Build
Connect & Complete
1

## Slide 3
Standard v Complex Applications
A standard application can essentially follow a simple application process with minimal optioneering and network study needs.
Examples that will tend to be standard are:
Single or a small number of new residential or business connections
A modest increase in capacity at a site (where the network is not constrained)
A small-midsized commercial connection (where the network is not constrained)
A residential or small-midsized commercial DG connection
A complex application requires additional work by, and time of, the EDB or service providers, to analyse information, assess network, scope options and complete studies. Project size or technical criteria may also qualify a project as needing additional work.
Examples that will tend to be complex are:
A large commercial or industrial customer
A utility scale solar or battery
A smaller project where it is identified the network may need investment to support
Standard
Complex
Our connection steps provide a brief introduction to the five key steps for your new network connection. The detailed activity, costs and timing differ between standard and complex applications. We indicate below what we would typically expect to be a standard and a complex connection.
2

## Slide 4
Connection steps For Standard connections
Understand your options, the process, timelines and application costs with our self-service support (e.g., website FAQs and resources) and/ or your service provider (e.g., builder, electrician or approved contractor whose costs you will pay). Start with our on-line guides.
Complete your application and/ or engage your service provider who will apply for your connection (e.g., if you are upgrading your existing connection or need power to your boundary).
We complete a high-level review of your application within 10 working days and may request more information.
Pay the application fee within 30 calendar days.
Where needed, we work with the service provider to design and tailor the solution, ensuring it meets your requirements.
Key steps are to review and approve the proposed plan, costs and/or agreement before proceeding and make payment.
You will usually be supplied a quote within 10 working days for a simple connection. Please pay within 55 working days before the quote expires.
Your approved service provider will deliver the agreed solution if any network works are required.
Work begins after you accept the quote and pay the invoice with connection generally completed within 6-8 weeks.
In parallel, your approved contractor will complete the service connection works you will contract with them and pay for.
Where your electrician is completing work, once we are advised the service is ready to connect and inspected, we connect within 10 working days.
When the connection is ready and inspected, you or your electrician can contact your retailer for metering to be installed (by their contractors). Provide your ICP number.
The approved contractor will e-mail a certificate of compliance.
Documentation may be required to finalise e.g., as-built designs, easements.
Level
1
3
Enquire & Discuss
Apply & Explore
Design & Approve
Deliver & Build
Connect & Complete
3

## Slide 5
Connection steps Complex
Understand your options, the process, timelines and application costs with our self-service support (e.g., web resources, capacity maps, FAQs) and/or your designer or approved contractor.
Where your application is complex (e.g., large and/or you have flexibility in your connection size or location), enquire if a free pre-application meeting suits you. Work agreed following this meeting (e.g., preliminary studies prior to your formal application) may incur costs.
Start with our on-line resources.
Complete your application and/or engage your service provider who will apply for your connection.
This step covers 1) initial application for major projects, 2) a high-level application review within 30 working days (we may request more information), 3) feasibility studies (we will agree costs with you), 4) concept design by us or an approved designer (that tells you your capital costs).
Some projects may need other steps e.g., consent status, easement or Transpower conditions advised.
We work with relevant parties to design the solution for your needs. This step covers 1) an agreement / network approval and customer terms acceptance to proceed for standard projects, 2) an initial agreement / approval to proceed for complex projects subject to more work, 3) detailed studies/ design (with costs), interim/ final application, network application approval and network quote/ customer acceptance for complex projects, 4) connection and works agreement, 5) payment and 6) final capacity reserved.
Interim application to approval is within 90 working days.
The service provider ( BEL staff member) will, where applicable, build, test and liven any agreed new network assets.
In parallel, your approved contractor will complete the service connection works you will contract with them and pay for.
When the connection is ready, your approved contractor can progress connection work including an authorised inspector and metering (with your retailer).
Complex connections may require specific commissioning steps and/or testing.
Documentation may be required to finalise e.g., as-built designs, easements, engineers sign-off, certificate of compliance.
Our guides / team or your service provider will inform you about these.
Level
1
3
Enquire & Discuss
Apply & Explore
Design & Approve
Deliver & Build
Connect & Complete
4